## Task
ID | Name | Group | Predecessors | Baseline Start | Baseline End | Duration | Resource Requirement
1 | Problem study | Manage | 24FS | 2023-11-26 08:00 | 2023-11-30 17:00 | 24 | Engineering Manager: Microsoft Project: 3, Google Trends: 4, Google Analytics: 4, Exel: 3
2 | Processmodels | Analysis | 1FS | 2023-12-01 08:00 | 2023-12-01 16:00 | 7 | Analyst programmer: UML: 5, OOD: 5, Visual Paradigm: 3, Visio: 4
3 | Conceptual datamodel | Analysis | 1FS | 2023-12-01 08:00 | 2023-12-01 17:00 | 8 | Analyst programmer: UML: 3, OOD: 2, Visual Paradigm: 2
4 | normalisation DB | Data | 2FS;3FS | 2023-12-02 08:00 | 2023-12-02 12:00 | 4 | Database administrator: MySQL: 4, SQL Mastery: 2
5 | Data map | Data | 4FS | 2023-12-02 13:00 | 2023-12-02 14:00 | 1 | Database administrator: MySQL: 1, SQL Server: 1
6 | Logic databasemodel | Data | 5FS | 2023-12-02 14:00 | 2023-12-02 16:00 | 2 | Database administrator: MySQL: 3 , SQL Server: 2, SQL Mastery: 1
7 | Software design (UML classdiagram) | Analysis | 2FS;3FS | 2023-12-02 08:00 | 2023-12-03 17:00 | 16 | Analyst programmer: UML: 4, OOD: 2, Visual Paradigm: 2
8 | Develop Database tables 1 | Data | 6FS | 2023-12-02 16:00 | 2023-12-03 14:00 | 6 | Database administrator: MySQL:4, SQL Server: 3
9 | Develop Database tables 2 | Data | 6FS | 2023-12-02 16:00 | 2023-12-03 16:00 | 8 | Database administrator: MySQL: 5, SQL Server: 5
10 | Design & Develop GUI 1 | Development Program | 7FS | 2023-12-06 08:00 | 2023-12-07 17:00 | 16 | Programmer: Java: 2, JavaScript: 3, React: 4, JavaFX: 5
11 | Design & Develop GUI 2 | Development Program | 7FS | 2023-12-06 08:00 | 2023-12-08 14:00 | 21 | Programmer: Java: 3, JavaScript: 4, React: 5, JavaFX: 4
12 | Develop SQL's 1 | Data | 8FS | 2023-12-03 14:00 | 2023-12-07 16:00 | 18 | Database administrator: MySQL: 4, SQL Server: 3, SQL Mastery: 3
13 | Develop SQL's 2 | Data | 9FS | 2023-12-03 16:00 | 2023-12-14 11:00 | 20 | Database administrator: MySQL: 5, SQL Server: 3, SQL Mastery: 4
14 | Debug SQL's 1 | Data | 12FS | 2023-12-07 16:00 | 2023-12-09 09:00 | 10 | Database administrator: MySQL: 2, SQL Server: 1, SQL Mastery: 2
15 | Debug SQL's 2 | Data | 13FS | 2023-12-08 11:00 | 2023-12-09 16:00 | 12 | Database administrator: MySQL: 3, SQL Server: 2, SQL Mastery: 2
16 | Implement SQL's in JAVA 1 | Development Program | 14FS | 2023-12-09 09:00 | 2023-12-09 10:00 | 1 | Programmer: Java: 3, OOP: 3, SQL: 4, JDBC: 3
17 | Implement SQL's in JAVA 2 | Development Program | 15FS | 2023-12-09 16:00 | 2023-12-09 17:00 | 1 | Programmer: Java: 4, OOP: 4, SQL: 5, JDBC: 4
18 | Develop program 1 | Development Program | 16FS;10FS | 2023-12-09 10:00 | 2023-12-14 10:00 | 24 | Programmer: Java: 4, OOP: 5
19 | Develop program 2 | Development Program | 17FS;11FS | 2023-12-10 08:00 | 2023-12-15 14:00 | 29 | Programmer: Java: 5, OOP: 5
20 | Testing & Debugging 1 | Testing | 18FS | 2023-12-14 10:00 | 2023-12-15 10:00 | 8 | Software Tester:Java: 3, OOP: 2, JUnit: 4
21 | Testing & Debugging 2 | Testing | 19FS | 2023-12-15 14:00 | 2023-12-16 14:00 | 8 | Software Tester:Java: 2, JUnit: 5
22 | Explore the market | Analysis |  | 2023-10-19 08:00 | 2023-11-01 17:00 | 50 | Engineering Manager: Microsoft Project: 4, Google Trends: 3, Google Analytics: 4, Exel: 2
23 | Set up a survey | Marketing | 22FS | 2023-11-02 08:00 | 2023-11-04 17:00 | 24 | Marketing Manager: Marketing Strategy: 4, Budget Management: 2, Exel: 3, Typeform: 3
24 | Analysis of the market | Sale | 23FS | 2023-11-05 08:00 | 2023-11-25 17:00 | 60 | Sales representatives: Marketing Strategy: 3, CRM: 5, Google Analytics: 5, SEMrush: 2, Statista: 4
25 | Design CD-box | Technical | 10FS;11FS | 2023-12-08 14:00 | 2023-12-22 14:00 | 75 | Technicians: Window Server: 2, Microsoft Window: 3, macOS: 3, CD Label Designer: 4, Virtual Box: 2
26 | Design CD-labels | Technical | 10FS;11FS | 2023-12-08 14:00 | 2023-12-22 14:00 | 70 | Technicians: Window Server: 3, Microsoft Window: 3, macOS: 3, CD Label Designer: 5, Virtual Box: 1
27 | Make up report + presentation Alpha version | Analysis | 20FS;21FS | 2023-12-16 14:00 | 2023-12-20 14:00 | 16 | Analyst programmer: UML: 4, OOD: 5, Visual Paradigm: 4
28 | Presentation Alpha Version | Manage | 27FS | 2023-12-20 14:00 | 2023-12-20 16:00 | 2 | Engineering Manager: Google Analytics: 2, Microsoft Project: 2
29 | Reading of management report + approval Alpha | Manage | 28FS | 2023-12-20 16:00 | 2023-12-21 12:00 | 5 | Engineering Manager: Microsoft Project: 2, Google Trends: 3, Google Analytics: 3
30 | Testing phase Alpha Version | Testing | 29FS | 2023-12-21 13:00 | 2023-12-24 12:00 | 24 | Software Tester: Java: 4, OOP: 2, JUnit: 5
31 | Fix outstanding problems from Alpha | Development Program | 30FS | 2023-12-24 13:00 | 2023-12-27 15:00 | 10 | Programmer: Java: 3, OOP: 3, JavaFX: 2, JUnit: 1
32 | Make up report + presentation Beta version | Analysis | 31FS | 2023-12-27 15:00 | 2023-12-28 15:00 | 8 | Analyst programmer: UML: 2, OOD: 1, Visual Paradigm: 3
33 | Presentation Beta Version | Development Program | 32FS | 2023-12-28 15:00 | 2023-12-28 17:00 | 2 | Programmer: Java: 4, OOP: 5, JavaFX: 1, JUnit: 1
34 | Reading of management report + approval Beta | Manage | 33FS | 2023-12-29 08:00 | 2023-12-29 14:00 | 5 | Engineering Manager: Microsoft Project: 2, Google Analytics: 3
35 | Launch and installation Beta Version | Technical | 34FS | 2023-12-29 14:00 | 2024-01-05 14:00 | 40 | Technicians: Window Server: 2, Microsoft Window: 2 ,macOS: 4, Virtual Box: 5
36 | Direct maillings | Marketing | 20FS;21FS | 2023-12-16 14:00 | 2023-12-16 16:00 | 2 | Marketing Manager:Marketing Strategy: 4
37 | Negotiate and buy server | Sale | 1FS | 2023-12-01 08:00 | 2023-12-02 17:00 | 80 | Sales representatives: Marketing Strategy: 3, CRM: 4, Google Analytics: 5, SEMrush: 3, Statista: 2
38 | Visitations by sales representatives | Marketing | 20FS;21FS | 2023-12-16 14:00 | 2023-12-30 14:00 | 16 | Marketing Manager: Marketing Strategy: 5, Budget Management: 4
39 | Negotiate and buy computer | Marketing | 1FS | 2023-12-01 08:00 | 2023-12-02 17:00 | 16 | Marketing Manager: Budget Management: 5
40 | Installation server | Technical | 35FS;39FS | 2023-12-29 14:00 | 2024-01-05 14:00 | 40 | Technicians: Window Server: 5
41 | Installation computer | Technical | 35FS;40FS | 2023-12-29 14:00 | 2024-01-05 14:00 | 40 | Technicians:Microsoft Window: 4, macOS: 3, Virtual Box: 3
ID | Name of tasks (sum of tasks = 41) | Predecessors | Predecessors | Baseline Start | Baseline End | Duration
2023-10-19 08:00
NHÓM CÔNG VIỆC
Development Program
ID | Name | Group | Predecessors | Baseline Start | Baseline End | Duration | Skill requirement
10 | Design & Develop GUI 1 | Development Program | 7FS | 2023-12-06 08:00 | 2023-12-07 17:00 | 16 | Programmer: Java: 2, JavaScript: 3, React: 4, JavaFX: 5
11 | Design & Develop GUI 2 | Development Program | 7FS | 2023-12-06 08:00 | 2023-12-08 14:00 | 21 | Programmer: Java: 3, JavaScript: 4, React: 5, JavaFX: 4
16 | Implement SQL's in JAVA 1 | Development Program | 14FS | 2023-12-09 09:00 | 2023-12-09 10:00 | 1 | Programmer: Java: 3, OOP: 3, SQL: 4, JDBC: 3
17 | Implement SQL's in JAVA 2 | Development Program | 15FS | 2023-12-09 16:00 | 2023-12-09 17:00 | 1 | Programmer: Java: 4, OOP: 4, SQL: 5, JDBC: 4
18 | Develop program 1 | Development Program | 16FS;10FS | 2023-12-09 10:00 | 2023-12-14 10:00 | 24 | Programmer: Java: 4, OOP: 5
19 | Develop program 2 | Development Program | 17FS;11FS | 2023-12-10 08:00 | 2023-12-15 14:00 | 29 | Programmer: Java: 5, OOP: 5
31 | Fix outstanding problems from Alpha | Development Program | 30FS | 2023-12-24 13:00 | 2023-12-27 15:00 | 10 | Programmer: Java: 3, OOP: 3, JavaFX: 2, JUnit: 1
33 | Presentation Beta Version | Development Program | 32FS | 2023-12-28 15:00 | 2023-12-28 17:00 | 2 | Programmer: Java: 4, OOP: 5, JavaFX: 1, JUnit: 1
ID | Name of tasks (sum of tasks = 8) | Groups | Predecessors | Baseline Start | Baseline End | Duration total: 104(hours)
Testing
ID | Name | Group | Predecessors | Baseline Start | Baseline End | Duration | Skill requirement
20 | Testing & Debugging 1 | Testing | 18FS | 2023-12-14 10:00 | 2023-12-15 10:00 | 8 | Software Tester:Java: 3, OOP: 2, Junit: 4
21 | Testing & Debugging 2 | Testing | 19FS | 2023-12-15 14:00 | 2023-12-16 14:00 | 8 | Software Tester:Java: 2, Junit: 5
30 | Testing phase Alpha Version | Testing | 29FS | 2023-12-21 13:00 | 2023-12-24 12:00 | 24 | Software Tester: Java: 4, OOP: 2, Junit: 5
ID | Name of tasks (sum of tasks = 3) | Groups | Predecessors | Baseline Start | Baseline End | Duration total: 40(hours)
Data
ID | Name | Group | Predecessors | Baseline Start | Baseline End | Duration | Skill requirement
4 | normalisation DB | Data | 2FS;3FS | 2023-12-02 08:00 | 2023-12-02 12:00 | 4 | Database administrator: MySQL: 4, SQL Mastery:2
5 | Data map | Data | 4FS | 2023-12-02 13:00 | 2023-12-02 14:00 | 1 | Database administrator: MySQL: 1, SQL Server: 1
6 | Logic databasemodel | Data | 5FS | 2023-12-02 14:00 | 2023-12-02 16:00 | 2 | Database administrator: MySQL: 3 , SQL Server: 2, SQL Mastery: 1
8 | Develop Database tables 1 | Data | 6FS | 2023-12-02 16:00 | 2023-12-03 14:00 | 6 | Database administrator: MySQL:4, SQL Server: 3
9 | Develop Database tables 2 | Data | 6FS | 2023-12-02 16:00 | 2023-12-03 16:00 | 8 | Database administrator: MySQL: 5, SQL Server: 5
12 | Develop SQL's 1 | Data | 8FS | 2023-12-03 14:00 | 2023-12-07 16:00 | 18 | Database administrator: MySQL: 4, SQL Server: 3, SQL Mastery: 3
13 | Develop SQL's 2 | Data | 9FS | 2023-12-03 16:00 | 2023-12-14 11:00 | 20 | Database administrator: MySQL: 5, SQL Server: 3, SQL Mastery: 4
14 | Debug SQL's 1 | Data | 12FS | 2023-12-07 16:00 | 2023-12-09 09:00 | 10 | Database administrator: MySQL: 2, SQL Server: 1, SQL Mastery: 2
15 | Debug SQL's 2 | Data | 13FS | 2023-12-08 11:00 | 2023-12-09 16:00 | 12 | Database administrator: MySQL: 3, SQL Server: 2, SQL Mastery: 2
ID | Name of tasks (sum of tasks = 9) | Group | Predecessors | Baseline Start | Baseline End | Duration total: 81(hours)
Manage
ID | Name | Group | Predecessors | Baseline Start | Baseline End | Duration | Skill requirement
1 | Problem study | Manage | 24FS | 2023-11-26 08:00 | 2023-11-30 17:00 | 24 | Engineering Manager: Microsoft Project: 3, Google Trends: 4, Google Analytics: 4, Exel: 3
22 | Explore the market | Analysis |  | 2023-10-19 08:00 | 2023-11-01 17:00 | 50 | Engineering Manager: Microsoft Project: 4, Google Trends: 3, Google Analytics: 4, Exel: 2
28 | Presentation Alpha Version | Manage | 27FS | 2023-12-20 14:00 | 2023-12-20 16:00 | 2 | Engineering Manager: Google Analytics: 2, Microsoft Project: 2
29 | Reading of management report + approval Alpha | Manage | 28FS | 2023-12-20 16:00 | 2023-12-21 12:00 | 5 | Engineering Manager: Microsoft Project: 2, Google Trends: 3, Google Analytics: 3
34 | Reading of management report + approval Beta | Manage | 33FS | 2023-12-29 08:00 | 2023-12-29 14:00 | 5 | Engineering Manager: Microsoft Project: 2, Google Analytics: 3
ID | Name of tasks (sum of tasks = 5) | Group | Predecessors | Baseline Start | Baseline End | Duration total: 116(hours)
Analysis
ID | Name | Group | Predecessors | Baseline Start | Baseline End | Duration | Skill requirement
2 | Processmodels | Analysis | 1FS | 2023-12-01 08:00 | 2023-12-01 16:00 | 7 | Analyst programmer: UML: 5, OOD: 5, Visual Paradigm: 3, Visio: 4
3 | Conceptual datamodel | Analysis | 1FS | 2023-12-01 08:00 | 2023-12-01 17:00 | 8 | Analyst programmer: UML: 3, OOD: 2, Visual Paradigm: 2
7 | Software design (UML classdiagram) | Analysis | 2FS;3FS | 2023-12-02 08:00 | 2023-12-03 17:00 | 16 | Analyst programmer: UML: 4, OOD: 2, Visual Paradigm: 2
27 | Make up report + presentation Alpha version | Analysis | 20FS;21FS | 2023-12-16 14:00 | 2023-12-20 14:00 | 16 | Analyst programmer: UML: 4, OOD: 5, Visual Paradigm: 4
32 | Make up report + presentation Beta version | Analysis | 31FS | 2023-12-27 15:00 | 2023-12-28 15:00 | 8 | Analyst programmer: UML: 2, OOD: 1, Visual Paradigm: 3
ID | Name of tasks (sum of tasks = 5) | Group | Predecessors | Baseline Start | Baseline End | Duration total: 55(hours)
Marketing
ID | Name | Group | Predecessors | Baseline Start | Baseline End | Duration | Skill requirement
23 | Set up a survey | Marketing | 22FS | 2023-11-02 08:00 | 2023-11-04 17:00 | 24 | Marketing Manager: Marketing Strategy: 4, Budget Management: 2, Exel: 3, Typeform: 3
36 | Direct maillings | Marketing | 20FS;21FS | 2023-12-16 14:00 | 2023-12-16 16:00 | 2 | Marketing Manager:Marketing Strategy: 4
38 | Visitations by sales representatives | Marketing | 20FS;21FS | 2023-12-16 14:00 | 2023-12-30 14:00 | 16 | Marketing Manager: Marketing Strategy: 5, Budget Management: 4
39 | Negotiate and buy computer | Marketing | 1FS | 2023-12-01 08:00 | 2023-12-02 17:00 | 16 | Marketing Manager: Budget Management: 5
ID | Name of tasks (sum of tasks = 4) | Group | Predecessors | Baseline Start | Baseline End | Duration total: 58(hours)
Sale
ID | Name | Group | Predecessors | Baseline Start | Baseline End | Duration | Skill requirement
24 | Analysis of the market | Sale | 23FS | 2023-11-05 08:00 | 2023-11-25 17:00 | 120 | Sales representatives: Marketing Strategy: 3, CRM: 5, GG Analytics: 5, SEMrush: 2, Statista: 4
37 | Negotiate and buy server | Sale | 1FS | 2023-12-01 08:00 | 2023-12-02 17:00 | 80 | Sales representatives: Marketing Strategy: 3 CRM: 4, Google Analytics: 5, SEMrush: 3, Statista: 2
ID | Name of tasks (sum of tasks = 2) | Group | Predecessors | Baseline Start | Baseline End | Duration total: 200(hours)
Technical
ID | Name | Group | Predecessors | Baseline Start | Baseline End | Duration | Skill requirement
25 | Design CD-box | Technical | 10FS;11FS | 2023-12-08 14:00 | 2023-12-22 14:00 | 80 | Technicians: Window Server: 2, Microsoft Window: 3, macOS: 3, CD Label Designer: 4, Virtual Box: 2
26 | Design CD-labels | Technical | 10FS;11FS | 2023-12-08 14:00 | 2023-12-22 14:00 | 80 | Technicians: Window Server: 3, Microsoft Window: 3, macOS: 3, CD Label Designer: 5, Virtual Box: 1
35 | Launch and installation Beta Version | Technical | 34FS | 2023-12-29 14:00 | 2024-01-05 14:00 | 40 | Technicians: Window Server: 2, Microsoft Window: 2 ,macOS: 4, Virtual Box: 5
40 | Installation server | Technical | 35FS;39FS | 2023-12-29 14:00 | 2024-01-05 14:00 | 40 | Technicians: Window Server: 5
41 | Installation computer | Technical | 35FS;40FS | 2023-12-29 14:00 | 2024-01-05 14:00 | 40 | Technicians:Microsoft Window: 4, macOS: 3, Virtual Box: 3
ID | Name of tasks (sum of tasks = 5) | Group | Predecessors | Baseline Start | Baseline End | Duration total: 280(hours)

## Resources
ID | Type | Description | Availability | Qualities | Skill Groups | Cost | Cost OT | ID | Type | Quantity | Skill | Groups Skill | ID | Type | Cost OT | Total Level/ Total Group Skills
1 | Programmer | Alex Johnson - 123 Main Street, Apt 4B, New York, NY 10001 | Yes | Java: 4, OOP: 2, JavaScript: 4, React: 5, JavaFX: 5, SQL: 1, JDBC: 0, JUnit: 1 | Development Program | 162 $ | 121$ | 1 | Engineering Manager | 1 | Microsoft Project, Google Trends, Google Analytics, Exel, Java, OOP | Manage | 1 | Programmers | 121$ | 0.55
2 | Programmer | Emily Davis - 456 Oak Avenue, Suite 302, Los Angeles, CA 90012 | Yes | Java: 4, OOP: 5, JavaScript: 1, React: 0, JavaFX: 1, SQL: 5, JDBC: 5, JUnit: 2 | Development Program | 165 $ | 124$ | 2 | Programmers | 4 | Java, OOP, JavaScript, React, JavaFX, SQL, JDBC, JUnit | Development Program | 2 | Programmers | 124$ | 0.575
3 | Programmer | Brandon Smith - 789 Pine Street, Unit 15, Chicago, IL 60601 | No | Java: 4, OOP: 2, JavaScript: 3, React: 3, JavaFX: 2, SQL: 1, JDBC: 0, JUnit: 2 | Development Program | 147 $ | 110$ | 3 | Database administrator | 2 | MySQL, SQL Server, SQL Mastery | Data | 3 | Programmers | 110$ | 0.425
4 | Programmer | Jessica Miller - 234 Elm Lane, Apt 7D, San Francisco, CA 94105 | Yes | Java: 5, OOP: 4, JavaScript: 3, React: 3, JavaFX: 3, SQL: 3, JDBC: 2, JUnit: 1 | Development Program | 168 $ | 126$ | 4 | Analyst programmer | 1 | UML, OOD, Visual Paradigm, Visio | Analysis | 4 | Programmers | 126$ | 0.6
5 | Engineering Manager | Kevin Wilson - 567 Maple Drive, Unit 22, Miami, FL 33130 | Yes | Microsoft Project: 4, Google Trends: 4, Google Analytics: 4, Exel: 3, Java: 3, OOP: 4 | Manage, Development Program | 342 $ | 256$ | 5 | Secretary | 1 | Google Forms, Exel | Manage | 5 | Engineering Manager | 256$ | 0.5 + 0.175
6 | Database administrator | Olivia White - 890 Cedar Street, Apt 10C, Austin, TX 78701 | Yes | MySQL: 5, SQL Server: 5, SQL Mastery: 4 | Data | 123$ | 92$ | 6 | Marketing Manager | 1 | Marketing Strategy, Budget Management, Exel, Typeform | Manage | 6 | Database administrator | 92$ | 0.933
7 | Database administrator | Ryan Taylor - 345 Birch Avenue, Unit 3, Seattle, WA 98101 | No | MySQL: 3, SQL Server: 5, SQL Mastery: 2 | Data | 101 $ | 82$ | 7 | Sales representatives | 2 | CRM, Google Analytics, SEMrush, Statista | Maketing | 7 | Database administrator | 82$ | 0.667
8 | Analyst programmer | Ashley Harris - 678 Pine Lane, Apt 8A, Boston, MA 02108 | Yes | UML: 5, OOD: 5, Visual Paradigm: 4, Visio: 4 | Analysis | 204 $ | 153$ | 8 | Technicians | 5 | Window Server, Microsoft Window, macOS, CD Label Designer, Virtual Box | Technical | 8 | Analyst programmer | 153$ | 0.9
9 | Secretary | Tyler Jackson - 901 Oak Court, Apt 12B, Denver, CO 80202 | Yes | CRM: 3, Google Analytics: 4, Statista: 3 | Marketing | 63 $ | 47$ | 9 | Project Manager | 1 | Microsoft Project, Google Trends, Google Analytics, Budget Management, Exel, Typeform | Manage | 9 | Secretary | 47$ | 0.4
10 | Marketing Manager | Natalie Martin - 234 Walnut Road, Unit 6, Atlanta, GA 30301 | Yes | Marketing Strategy: 5, Budget Management: 5, Exel: 4, Typeform: 3 | Manage, Marketing | 243 $ | 182$ | 10 | Software Tester | 2 | Java, OOP, JUnit | Development Program | 10 | Marketing Manager | 182$ | 0.2 + 0.4
11 | Sales representatives | Samantha Brown - 890 Birch Drive, Suite 18, Phoenix, AZ 85001 | Yes | Marketing Strategy: 3, CRM: 5, Google Analytics: 5, SEMrush: 2, Statista: 5 | Marketing | 91 $ | 68$ |  |  | 20 |  |  | 11 | Sales representatives | 68$ | 0.8
12 | Sales representatives | Jordan Garcia - 123 Pine Lane, Apt 5C, Philadelphia, PA 19103 | Yes | Marketing Strategy: 3, CRM: 4 , Google Analytics: 5, SEMrush: 3 , Statista: 3 | Marketing | 85 $ | 64$ | [5 empty] | 12 | Sales representatives | 64$ | 0.72
13 | Technicians | Morgan Clark - 456 Elm Street, Apt 14A, San Diego, CA 92101 | Yes | Window Server: 2, Microsoft Window: 2 ,macOS: 4, CD Label Designer: 2, Virtual Box: 5 | Technical | 145 $ | 109$ | Cách tính lương |  |  | Luật tính lương |  | 13 | Technicians | 109$ | 0.75
14 | Technicians | Justin Hill - 789 Oak Avenue, Unit 20, Detroit, MI 48201 | Yes | Window Server: 0, Microsoft Window: 4, macOS: 3, CD Label Designer: 0, Virtual Box: 3 | Technical | 110 $ | 82$ |  |  |  | Cost = Base cost * { Complexity + [Total Level skill / ( Max level skill * Total group skills ) ]} |  | 14 | Technicians | 82$ | 0.4
15 | Technicians | Lauren Martinez - 234 Cedar Road, Apt 11B, Houston, TX 77001 | Yes | Window Server: 2, Microsoft Window: 3 ,macOS: 3, CD Label Designer: 4, Virtual Box: 2 | Technical | 126 $ | 94$ |  |  |  | Cost OT = Cost / 2 x 1.5 |  | 15 | Technicians | 94$ | 0.56
16 | Technicians | Derek Adams - 567 Walnut Drive, Suite 25, Nashville, TN 37201 | Yes | Window Server: 5, Microsoft Window: 2, macOS: 2, CD Label Designer: 0, Virtual Box: 2 | Technical | 114 $ | 85$ | [5 empty] | 16 | Technicians | 85$ | 0.44
17 | Technicians | Brooke Turner - 890 Maple Court, Apt 16D, Minneapolis, MN 55401 | Yes | Window Server: 3, Microsoft Window: 3, macOS: 3, CD Label Designer: 5, Virtual Box: 1 | Technical | 126 $ | 94$ | Groups Skill | Complexity | Base Cost |  |  | 17 | Technicians | 94$ | 0.56
18 | Project Manager | Ethan Johnson - 123 Pine Street, Apt 8C, San Francisco, CA 94105 |  | Microsoft Project: 4, Google Trends: 4, Google Analytics: 5, Budget Management: 3, Exel: 2, Typeform: 3 | Manage | 225 $ | 169$ | Manage | 1 | 150 $ / day | Microsoft Project, Google Trends, Google Analytics, Budget Management, Exel, Typeform |  | 18 | Project Manager | 169$ | 0.7
19 | Software Tester | Chloe Davis - 456 Maple Lane, Unit 11, Seattle, WA 98101 |  | Java: 4 , OOP: 3, JUnit: 5 | Development Program | 132 $ | 99$ | Development Program | 0.8 | 120 $ / day | Java, OOP, JavaScript, React, JavaFX, SQL, JDBC, JUnit |  | 19 | Software Tester | 99$ | 0.3
20 | Software Tester | Noah Smith - 789 Elm Avenue, Apt 6B, Los Angeles, CA 90012 |  | Java: 2, OOP: 3, JUnit: 4 | Development Program | 123 $ | 92$ | Data | 0.6 | 80 $ / day | MySQL, SQL Server, SQL Mastery |  | 20 | Software Tester | 92$ | 0.225
[8 empty] | Maketing | 0.5 | 70 $ / day | Marketing Strategy, CRM, Google Analytics, SEMrush, Statista
[8 empty] | Technical | 0.7 | 100 $ / day | Window Server, Microsoft Window, macOS, CD Label Designer, Virtual Box
[8 empty] | Analysis | 0.8 | 120 $ / day | UML, OOD, Visual Paradigm, Visio

## Timeframe
start | end | type | ID_1 | ID_2 | ID_3 | ID_4 | ID_5 | ID_6 | ID_7 | ID_8 | ID_9 | ID_10 | ID_11 | ID_12 | ID_13 | ID_14 | ID_15 | ID_16 | ID_17 | ID_18 | ID_19 | ID_20
2023-01-01 08:00 | 2023-01-02 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-02 08:00 | 2023-01-02 12:00 | Morning shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0
2023-01-02 12:00 | 2023-01-02 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-02 13:00 | 2023-01-02 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-01-02 17:00 | 2023-01-02 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-02 21:00 | 2023-01-03 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-03 08:00 | 2023-01-03 12:00 | Morning shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0
2023-01-03 12:00 | 2023-01-03 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-03 13:00 | 2023-01-03 17:00 | Afternoon shift | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-03 17:00 | 2023-01-04 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-04 08:00 | 2023-01-04 12:00 | Morning shift | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
2023-01-04 12:00 | 2023-01-04 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-04 13:00 | 2023-01-04 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-04 17:00 | 2023-01-04 21:00 | Overtime | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-04 21:00 | 2023-01-05 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-05 08:00 | 2023-01-05 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1
2023-01-05 12:00 | 2023-01-05 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-05 13:00 | 2023-01-05 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-05 17:00 | 2023-01-06 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-06 08:00 | 2023-01-06 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1
2023-01-06 12:00 | 2023-01-06 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-06 13:00 | 2023-01-06 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1
2023-01-06 17:00 | 2023-01-06 21:00 | Overtime | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1
2023-01-06 21:00 | 2023-01-07 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-07 08:00 | 2023-01-08 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-08 08:00 | 2023-01-09 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-09 08:00 | 2023-01-09 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-09 12:00 | 2023-01-09 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-09 13:00 | 2023-01-09 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0
2023-01-09 17:00 | 2023-01-10 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-10 08:00 | 2023-01-10 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1
2023-01-10 12:00 | 2023-01-10 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-10 13:00 | 2023-01-10 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-10 17:00 | 2023-01-10 21:00 | Overtime | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-01-10 21:00 | 2023-01-11 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-11 08:00 | 2023-01-11 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-11 12:00 | 2023-01-11 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-11 13:00 | 2023-01-11 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-11 17:00 | 2023-01-12 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-12 08:00 | 2023-01-12 12:00 | Morning shift | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-12 12:00 | 2023-01-12 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-12 13:00 | 2023-01-12 17:00 | Afternoon shift | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-12 17:00 | 2023-01-12 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-12 21:00 | 2023-01-13 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-13 08:00 | 2023-01-13 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1
2023-01-13 12:00 | 2023-01-13 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-13 13:00 | 2023-01-13 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0
2023-01-13 17:00 | 2023-01-14 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-14 08:00 | 2023-01-15 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-15 08:00 | 2023-01-16 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-16 08:00 | 2023-01-16 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-16 12:00 | 2023-01-16 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-16 13:00 | 2023-01-16 17:00 | Afternoon shift | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1
2023-01-16 17:00 | 2023-01-17 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-17 08:00 | 2023-01-17 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-17 12:00 | 2023-01-17 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-17 13:00 | 2023-01-17 17:00 | Afternoon shift | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1
2023-01-17 17:00 | 2023-01-18 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-18 08:00 | 2023-01-18 12:00 | Morning shift | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1
2023-01-18 12:00 | 2023-01-18 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-18 13:00 | 2023-01-18 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-18 17:00 | 2023-01-19 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-19 08:00 | 2023-01-19 12:00 | Morning shift | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-01-19 12:00 | 2023-01-19 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-19 13:00 | 2023-01-19 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-19 17:00 | 2023-01-19 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0
2023-01-19 21:00 | 2023-01-20 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-20 08:00 | 2023-01-20 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1
2023-01-20 12:00 | 2023-01-20 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-20 13:00 | 2023-01-20 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-20 17:00 | 2023-01-20 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1
2023-01-20 21:00 | 2023-01-21 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-21 08:00 | 2023-01-22 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-22 08:00 | 2023-01-23 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-23 08:00 | 2023-01-23 12:00 | Morning shift | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1
2023-01-23 12:00 | 2023-01-23 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-23 13:00 | 2023-01-23 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-23 17:00 | 2023-01-24 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-24 08:00 | 2023-01-24 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-24 12:00 | 2023-01-24 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-24 13:00 | 2023-01-24 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-24 17:00 | 2023-01-25 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-25 08:00 | 2023-01-25 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-25 12:00 | 2023-01-25 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-25 13:00 | 2023-01-25 17:00 | Afternoon shift | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1
2023-01-25 17:00 | 2023-01-25 21:00 | Overtime | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-25 21:00 | 2023-01-26 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-26 08:00 | 2023-01-26 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-26 12:00 | 2023-01-26 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-26 13:00 | 2023-01-26 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-26 17:00 | 2023-01-26 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-01-26 21:00 | 2023-01-27 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-27 08:00 | 2023-01-27 12:00 | Morning shift | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1
2023-01-27 12:00 | 2023-01-27 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-27 13:00 | 2023-01-27 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-27 17:00 | 2023-01-28 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-28 08:00 | 2023-01-29 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-29 08:00 | 2023-01-30 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-30 08:00 | 2023-01-30 12:00 | Morning shift | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-30 12:00 | 2023-01-30 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-30 13:00 | 2023-01-30 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
2023-01-30 17:00 | 2023-01-30 21:00 | Overtime | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0
2023-01-30 21:00 | 2023-01-31 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-31 08:00 | 2023-01-31 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-31 12:00 | 2023-01-31 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-01-31 13:00 | 2023-01-31 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-01-31 17:00 | 2023-01-31 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
2023-01-31 21:00 | 2023-02-01 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-01 08:00 | 2023-02-01 12:00 | Morning shift | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
2023-02-01 12:00 | 2023-02-01 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-01 13:00 | 2023-02-01 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0
2023-02-01 17:00 | 2023-02-01 21:00 | Overtime | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1
2023-02-01 21:00 | 2023-02-02 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-02 08:00 | 2023-02-02 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1
2023-02-02 12:00 | 2023-02-02 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-02 13:00 | 2023-02-02 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-02-02 17:00 | 2023-02-02 21:00 | Overtime | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1
2023-02-02 21:00 | 2023-02-03 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-03 08:00 | 2023-02-03 12:00 | Morning shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1
2023-02-03 12:00 | 2023-02-03 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-03 13:00 | 2023-02-03 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-02-03 17:00 | 2023-02-04 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-04 08:00 | 2023-02-05 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-05 08:00 | 2023-02-06 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-06 08:00 | 2023-02-06 12:00 | Morning shift | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1
2023-02-06 12:00 | 2023-02-06 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-06 13:00 | 2023-02-06 17:00 | Afternoon shift | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-02-06 17:00 | 2023-02-07 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-07 08:00 | 2023-02-07 12:00 | Morning shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
2023-02-07 12:00 | 2023-02-07 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-07 13:00 | 2023-02-07 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-02-07 17:00 | 2023-02-07 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1
2023-02-07 21:00 | 2023-02-08 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-08 08:00 | 2023-02-08 12:00 | Morning shift | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1
2023-02-08 12:00 | 2023-02-08 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-08 13:00 | 2023-02-08 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1
2023-02-08 17:00 | 2023-02-09 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-09 08:00 | 2023-02-09 12:00 | Morning shift | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-02-09 12:00 | 2023-02-09 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-09 13:00 | 2023-02-09 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-02-09 17:00 | 2023-02-10 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-10 08:00 | 2023-02-10 12:00 | Morning shift | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1
2023-02-10 12:00 | 2023-02-10 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-10 13:00 | 2023-02-10 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0
2023-02-10 17:00 | 2023-02-10 21:00 | Overtime | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-02-10 21:00 | 2023-02-11 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-11 08:00 | 2023-02-12 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-12 08:00 | 2023-02-13 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-13 08:00 | 2023-02-13 12:00 | Morning shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-02-13 12:00 | 2023-02-13 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-13 13:00 | 2023-02-13 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1
2023-02-13 17:00 | 2023-02-13 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-02-13 21:00 | 2023-02-14 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-14 08:00 | 2023-02-14 12:00 | Morning shift | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-02-14 12:00 | 2023-02-14 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-14 13:00 | 2023-02-14 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-02-14 17:00 | 2023-02-14 21:00 | Overtime | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
2023-02-14 21:00 | 2023-02-15 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-15 08:00 | 2023-02-15 12:00 | Morning shift | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0
2023-02-15 12:00 | 2023-02-15 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-15 13:00 | 2023-02-15 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
2023-02-15 17:00 | 2023-02-15 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-02-15 21:00 | 2023-02-16 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-16 08:00 | 2023-02-16 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-02-16 12:00 | 2023-02-16 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-16 13:00 | 2023-02-16 17:00 | Afternoon shift | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1
2023-02-16 17:00 | 2023-02-16 21:00 | Overtime | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1
2023-02-16 21:00 | 2023-02-17 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-17 08:00 | 2023-02-17 12:00 | Morning shift | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-02-17 12:00 | 2023-02-17 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-17 13:00 | 2023-02-17 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-02-17 17:00 | 2023-02-18 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-18 08:00 | 2023-02-19 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-19 08:00 | 2023-02-20 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-20 08:00 | 2023-02-20 12:00 | Morning shift | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
2023-02-20 12:00 | 2023-02-20 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-20 13:00 | 2023-02-20 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-02-20 17:00 | 2023-02-21 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-21 08:00 | 2023-02-21 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 0
2023-02-21 12:00 | 2023-02-21 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-21 13:00 | 2023-02-21 17:00 | Afternoon shift | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-02-21 17:00 | 2023-02-22 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-22 08:00 | 2023-02-22 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-02-22 12:00 | 2023-02-22 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-22 13:00 | 2023-02-22 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1
2023-02-22 17:00 | 2023-02-23 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-23 08:00 | 2023-02-23 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1
2023-02-23 12:00 | 2023-02-23 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-23 13:00 | 2023-02-23 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1
2023-02-23 17:00 | 2023-02-24 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-24 08:00 | 2023-02-24 12:00 | Morning shift | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-02-24 12:00 | 2023-02-24 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-24 13:00 | 2023-02-24 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-02-24 17:00 | 2023-02-24 21:00 | Overtime | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-02-24 21:00 | 2023-02-25 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-25 08:00 | 2023-02-26 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-26 08:00 | 2023-02-27 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-27 08:00 | 2023-02-27 12:00 | Morning shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-02-27 12:00 | 2023-02-27 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-27 13:00 | 2023-02-27 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-02-27 17:00 | 2023-02-28 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-28 08:00 | 2023-02-28 12:00 | Morning shift | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
2023-02-28 12:00 | 2023-02-28 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-02-28 13:00 | 2023-02-28 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
2023-02-28 17:00 | 2023-02-28 21:00 | Overtime | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-02-28 21:00 | 2023-03-01 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-01 08:00 | 2023-03-01 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1
2023-03-01 12:00 | 2023-03-01 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-01 13:00 | 2023-03-01 17:00 | Afternoon shift | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1
2023-03-01 17:00 | 2023-03-01 21:00 | Overtime | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-03-01 21:00 | 2023-03-02 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-02 08:00 | 2023-03-02 12:00 | Morning shift | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-02 12:00 | 2023-03-02 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-02 13:00 | 2023-03-02 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-02 17:00 | 2023-03-03 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-03 08:00 | 2023-03-03 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-03 12:00 | 2023-03-03 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-03 13:00 | 2023-03-03 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-03 17:00 | 2023-03-04 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-04 08:00 | 2023-03-05 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-05 08:00 | 2023-03-06 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-06 08:00 | 2023-03-06 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-06 12:00 | 2023-03-06 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-06 13:00 | 2023-03-06 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-06 17:00 | 2023-03-06 21:00 | Overtime | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
2023-03-06 21:00 | 2023-03-07 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-07 08:00 | 2023-03-07 12:00 | Morning shift | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-07 12:00 | 2023-03-07 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-07 13:00 | 2023-03-07 17:00 | Afternoon shift | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-07 17:00 | 2023-03-08 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-08 08:00 | 2023-03-08 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-08 12:00 | 2023-03-08 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-08 13:00 | 2023-03-08 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1
2023-03-08 17:00 | 2023-03-09 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-09 08:00 | 2023-03-09 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-03-09 12:00 | 2023-03-09 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-09 13:00 | 2023-03-09 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-03-09 17:00 | 2023-03-09 21:00 | Overtime | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-03-09 21:00 | 2023-03-10 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-10 08:00 | 2023-03-10 12:00 | Morning shift | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-10 12:00 | 2023-03-10 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-10 13:00 | 2023-03-10 17:00 | Afternoon shift | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-10 17:00 | 2023-03-10 21:00 | Overtime | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
2023-03-10 21:00 | 2023-03-11 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-11 08:00 | 2023-03-12 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-12 08:00 | 2023-03-13 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-13 08:00 | 2023-03-13 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-03-13 12:00 | 2023-03-13 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-13 13:00 | 2023-03-13 17:00 | Afternoon shift | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0
2023-03-13 17:00 | 2023-03-14 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-14 08:00 | 2023-03-14 12:00 | Morning shift | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-14 12:00 | 2023-03-14 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-14 13:00 | 2023-03-14 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-14 17:00 | 2023-03-14 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1
2023-03-14 21:00 | 2023-03-15 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-15 08:00 | 2023-03-15 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1
2023-03-15 12:00 | 2023-03-15 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-15 13:00 | 2023-03-15 17:00 | Afternoon shift | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1
2023-03-15 17:00 | 2023-03-16 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-16 08:00 | 2023-03-16 12:00 | Morning shift | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1
2023-03-16 12:00 | 2023-03-16 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-16 13:00 | 2023-03-16 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1
2023-03-16 17:00 | 2023-03-16 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1
2023-03-16 21:00 | 2023-03-17 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-17 08:00 | 2023-03-17 12:00 | Morning shift | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-17 12:00 | 2023-03-17 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-17 13:00 | 2023-03-17 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-03-17 17:00 | 2023-03-18 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-18 08:00 | 2023-03-19 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-19 08:00 | 2023-03-20 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-20 08:00 | 2023-03-20 12:00 | Morning shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-20 12:00 | 2023-03-20 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-20 13:00 | 2023-03-20 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-20 17:00 | 2023-03-21 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-21 08:00 | 2023-03-21 12:00 | Morning shift | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-21 12:00 | 2023-03-21 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-21 13:00 | 2023-03-21 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-03-21 17:00 | 2023-03-21 21:00 | Overtime | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-21 21:00 | 2023-03-22 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-22 08:00 | 2023-03-22 12:00 | Morning shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-22 12:00 | 2023-03-22 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-22 13:00 | 2023-03-22 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1
2023-03-22 17:00 | 2023-03-22 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-22 21:00 | 2023-03-23 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-23 08:00 | 2023-03-23 12:00 | Morning shift | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-03-23 12:00 | 2023-03-23 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-23 13:00 | 2023-03-23 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-23 17:00 | 2023-03-23 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-23 21:00 | 2023-03-24 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-24 08:00 | 2023-03-24 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-24 12:00 | 2023-03-24 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-24 13:00 | 2023-03-24 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-24 17:00 | 2023-03-25 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-25 08:00 | 2023-03-26 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-26 08:00 | 2023-03-27 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-27 08:00 | 2023-03-27 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1
2023-03-27 12:00 | 2023-03-27 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-27 13:00 | 2023-03-27 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-27 17:00 | 2023-03-27 21:00 | Overtime | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-27 21:00 | 2023-03-28 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-28 08:00 | 2023-03-28 12:00 | Morning shift | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-28 12:00 | 2023-03-28 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-28 13:00 | 2023-03-28 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0
2023-03-28 17:00 | 2023-03-29 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-29 08:00 | 2023-03-29 12:00 | Morning shift | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-29 12:00 | 2023-03-29 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-29 13:00 | 2023-03-29 17:00 | Afternoon shift | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-29 17:00 | 2023-03-30 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-30 08:00 | 2023-03-30 12:00 | Morning shift | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
2023-03-30 12:00 | 2023-03-30 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-30 13:00 | 2023-03-30 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-30 17:00 | 2023-03-31 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-31 08:00 | 2023-03-31 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
2023-03-31 12:00 | 2023-03-31 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-03-31 13:00 | 2023-03-31 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-03-31 17:00 | 2023-04-01 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-01 08:00 | 2023-04-02 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-02 08:00 | 2023-04-03 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-03 08:00 | 2023-04-03 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0
2023-04-03 12:00 | 2023-04-03 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-03 13:00 | 2023-04-03 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0
2023-04-03 17:00 | 2023-04-04 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-04 08:00 | 2023-04-04 12:00 | Morning shift | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1
2023-04-04 12:00 | 2023-04-04 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-04 13:00 | 2023-04-04 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-04-04 17:00 | 2023-04-04 21:00 | Overtime | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1
2023-04-04 21:00 | 2023-04-05 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-05 08:00 | 2023-04-05 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1
2023-04-05 12:00 | 2023-04-05 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-05 13:00 | 2023-04-05 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-04-05 17:00 | 2023-04-06 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-06 08:00 | 2023-04-06 12:00 | Morning shift | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-04-06 12:00 | 2023-04-06 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-06 13:00 | 2023-04-06 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1
2023-04-06 17:00 | 2023-04-06 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-04-06 21:00 | 2023-04-07 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-07 08:00 | 2023-04-07 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1
2023-04-07 12:00 | 2023-04-07 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-07 13:00 | 2023-04-07 17:00 | Afternoon shift | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-04-07 17:00 | 2023-04-08 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-08 08:00 | 2023-04-09 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-09 08:00 | 2023-04-10 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-10 08:00 | 2023-04-10 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-04-10 12:00 | 2023-04-10 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-10 13:00 | 2023-04-10 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-04-10 17:00 | 2023-04-11 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-11 08:00 | 2023-04-11 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-04-11 12:00 | 2023-04-11 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-11 13:00 | 2023-04-11 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1
2023-04-11 17:00 | 2023-04-12 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-12 08:00 | 2023-04-12 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-04-12 12:00 | 2023-04-12 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-12 13:00 | 2023-04-12 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-04-12 17:00 | 2023-04-12 21:00 | Overtime | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
2023-04-12 21:00 | 2023-04-13 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-13 08:00 | 2023-04-13 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-04-13 12:00 | 2023-04-13 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-13 13:00 | 2023-04-13 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0
2023-04-13 17:00 | 2023-04-14 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-14 08:00 | 2023-04-14 12:00 | Morning shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
2023-04-14 12:00 | 2023-04-14 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-14 13:00 | 2023-04-14 17:00 | Afternoon shift | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-04-14 17:00 | 2023-04-15 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-15 08:00 | 2023-04-16 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-16 08:00 | 2023-04-17 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-17 08:00 | 2023-04-17 12:00 | Morning shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
2023-04-17 12:00 | 2023-04-17 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-17 13:00 | 2023-04-17 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0
2023-04-17 17:00 | 2023-04-17 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-04-17 21:00 | 2023-04-18 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-18 08:00 | 2023-04-18 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-04-18 12:00 | 2023-04-18 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-18 13:00 | 2023-04-18 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1
2023-04-18 17:00 | 2023-04-19 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-19 08:00 | 2023-04-19 12:00 | Morning shift | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1
2023-04-19 12:00 | 2023-04-19 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-19 13:00 | 2023-04-19 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-04-19 17:00 | 2023-04-20 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-20 08:00 | 2023-04-20 12:00 | Morning shift | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1
2023-04-20 12:00 | 2023-04-20 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-20 13:00 | 2023-04-20 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-04-20 17:00 | 2023-04-20 21:00 | Overtime | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
2023-04-20 21:00 | 2023-04-21 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-21 08:00 | 2023-04-21 12:00 | Morning shift | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-04-21 12:00 | 2023-04-21 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-21 13:00 | 2023-04-21 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1
2023-04-21 17:00 | 2023-04-22 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-22 08:00 | 2023-04-23 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-23 08:00 | 2023-04-24 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-24 08:00 | 2023-04-24 12:00 | Morning shift | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
2023-04-24 12:00 | 2023-04-24 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-24 13:00 | 2023-04-24 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1
2023-04-24 17:00 | 2023-04-25 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-25 08:00 | 2023-04-25 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-04-25 12:00 | 2023-04-25 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-25 13:00 | 2023-04-25 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1
2023-04-25 17:00 | 2023-04-26 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-26 08:00 | 2023-04-26 12:00 | Morning shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-04-26 12:00 | 2023-04-26 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-26 13:00 | 2023-04-26 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1
2023-04-26 17:00 | 2023-04-26 21:00 | Overtime | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-04-26 21:00 | 2023-04-27 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-27 08:00 | 2023-04-27 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1
2023-04-27 12:00 | 2023-04-27 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-27 13:00 | 2023-04-27 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1
2023-04-27 17:00 | 2023-04-27 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
2023-04-27 21:00 | 2023-04-28 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-28 08:00 | 2023-04-28 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-04-28 12:00 | 2023-04-28 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-28 13:00 | 2023-04-28 17:00 | Afternoon shift | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-04-28 17:00 | 2023-04-28 21:00 | Overtime | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1
2023-04-28 21:00 | 2023-04-29 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-29 08:00 | 2023-04-30 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-04-30 08:00 | 2023-05-01 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-01 08:00 | 2023-05-01 12:00 | Morning shift | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-05-01 12:00 | 2023-05-01 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-01 13:00 | 2023-05-01 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1
2023-05-01 17:00 | 2023-05-02 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-02 08:00 | 2023-05-02 12:00 | Morning shift | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-05-02 12:00 | 2023-05-02 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-02 13:00 | 2023-05-02 17:00 | Afternoon shift | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-05-02 17:00 | 2023-05-03 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-03 08:00 | 2023-05-03 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
2023-05-03 12:00 | 2023-05-03 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-03 13:00 | 2023-05-03 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-05-03 17:00 | 2023-05-04 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-04 08:00 | 2023-05-04 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-05-04 12:00 | 2023-05-04 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-04 13:00 | 2023-05-04 17:00 | Afternoon shift | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1
2023-05-04 17:00 | 2023-05-04 21:00 | Overtime | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-05-04 21:00 | 2023-05-05 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-05 08:00 | 2023-05-05 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-05-05 12:00 | 2023-05-05 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-05 13:00 | 2023-05-05 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
2023-05-05 17:00 | 2023-05-06 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-06 08:00 | 2023-05-07 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-07 08:00 | 2023-05-08 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-08 08:00 | 2023-05-08 12:00 | Morning shift | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0
2023-05-08 12:00 | 2023-05-08 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-08 13:00 | 2023-05-08 17:00 | Afternoon shift | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-05-08 17:00 | 2023-05-09 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-09 08:00 | 2023-05-09 12:00 | Morning shift | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
2023-05-09 12:00 | 2023-05-09 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-09 13:00 | 2023-05-09 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1
2023-05-09 17:00 | 2023-05-09 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-05-09 21:00 | 2023-05-10 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-10 08:00 | 2023-05-10 12:00 | Morning shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
2023-05-10 12:00 | 2023-05-10 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-10 13:00 | 2023-05-10 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1
2023-05-10 17:00 | 2023-05-10 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-05-10 21:00 | 2023-05-11 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-11 08:00 | 2023-05-11 12:00 | Morning shift | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1
2023-05-11 12:00 | 2023-05-11 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-11 13:00 | 2023-05-11 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0
2023-05-11 17:00 | 2023-05-11 21:00 | Overtime | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1
2023-05-11 21:00 | 2023-05-12 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-12 08:00 | 2023-05-12 12:00 | Morning shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
2023-05-12 12:00 | 2023-05-12 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-12 13:00 | 2023-05-12 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1
2023-05-12 17:00 | 2023-05-12 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-05-12 21:00 | 2023-05-13 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-13 08:00 | 2023-05-14 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-14 08:00 | 2023-05-15 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-15 08:00 | 2023-05-15 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1
2023-05-15 12:00 | 2023-05-15 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-15 13:00 | 2023-05-15 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1
2023-05-15 17:00 | 2023-05-15 21:00 | Overtime | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0
2023-05-15 21:00 | 2023-05-16 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-16 08:00 | 2023-05-16 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
2023-05-16 12:00 | 2023-05-16 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-16 13:00 | 2023-05-16 17:00 | Afternoon shift | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
2023-05-16 17:00 | 2023-05-16 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1
2023-05-16 21:00 | 2023-05-17 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-17 08:00 | 2023-05-17 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-05-17 12:00 | 2023-05-17 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-17 13:00 | 2023-05-17 17:00 | Afternoon shift | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-05-17 17:00 | 2023-05-18 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-18 08:00 | 2023-05-18 12:00 | Morning shift | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-05-18 12:00 | 2023-05-18 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-18 13:00 | 2023-05-18 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1
2023-05-18 17:00 | 2023-05-18 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1
2023-05-18 21:00 | 2023-05-19 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-19 08:00 | 2023-05-19 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1
2023-05-19 12:00 | 2023-05-19 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-19 13:00 | 2023-05-19 17:00 | Afternoon shift | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-05-19 17:00 | 2023-05-20 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-20 08:00 | 2023-05-21 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-21 08:00 | 2023-05-22 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-22 08:00 | 2023-05-22 12:00 | Morning shift | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1
2023-05-22 12:00 | 2023-05-22 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-22 13:00 | 2023-05-22 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-05-22 17:00 | 2023-05-22 21:00 | Overtime | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-05-22 21:00 | 2023-05-23 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-23 08:00 | 2023-05-23 12:00 | Morning shift | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-05-23 12:00 | 2023-05-23 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-23 13:00 | 2023-05-23 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1
2023-05-23 17:00 | 2023-05-23 21:00 | Overtime | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-05-23 21:00 | 2023-05-24 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-24 08:00 | 2023-05-24 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1
2023-05-24 12:00 | 2023-05-24 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-24 13:00 | 2023-05-24 17:00 | Afternoon shift | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-05-24 17:00 | 2023-05-25 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-25 08:00 | 2023-05-25 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1
2023-05-25 12:00 | 2023-05-25 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-25 13:00 | 2023-05-25 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-05-25 17:00 | 2023-05-26 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-26 08:00 | 2023-05-26 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1
2023-05-26 12:00 | 2023-05-26 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-26 13:00 | 2023-05-26 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-05-26 17:00 | 2023-05-26 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1
2023-05-26 21:00 | 2023-05-27 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-27 08:00 | 2023-05-28 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-28 08:00 | 2023-05-29 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-29 08:00 | 2023-05-29 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1
2023-05-29 12:00 | 2023-05-29 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-29 13:00 | 2023-05-29 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-05-29 17:00 | 2023-05-30 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-30 08:00 | 2023-05-30 12:00 | Morning shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-05-30 12:00 | 2023-05-30 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-30 13:00 | 2023-05-30 17:00 | Afternoon shift | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-05-30 17:00 | 2023-05-30 21:00 | Overtime | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-05-30 21:00 | 2023-05-31 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-31 08:00 | 2023-05-31 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1
2023-05-31 12:00 | 2023-05-31 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-05-31 13:00 | 2023-05-31 17:00 | Afternoon shift | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-05-31 17:00 | 2023-06-01 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-01 08:00 | 2023-06-01 12:00 | Morning shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-06-01 12:00 | 2023-06-01 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-01 13:00 | 2023-06-01 17:00 | Afternoon shift | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-06-01 17:00 | 2023-06-01 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1
2023-06-01 21:00 | 2023-06-02 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-02 08:00 | 2023-06-02 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
2023-06-02 12:00 | 2023-06-02 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-02 13:00 | 2023-06-02 17:00 | Afternoon shift | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-06-02 17:00 | 2023-06-02 21:00 | Overtime | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1
2023-06-02 21:00 | 2023-06-03 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-03 08:00 | 2023-06-04 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-04 08:00 | 2023-06-05 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-05 08:00 | 2023-06-05 12:00 | Morning shift | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
2023-06-05 12:00 | 2023-06-05 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-05 13:00 | 2023-06-05 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-06-05 17:00 | 2023-06-05 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-06-05 21:00 | 2023-06-06 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-06 08:00 | 2023-06-06 12:00 | Morning shift | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
2023-06-06 12:00 | 2023-06-06 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-06 13:00 | 2023-06-06 17:00 | Afternoon shift | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-06-06 17:00 | 2023-06-07 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-07 08:00 | 2023-06-07 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-06-07 12:00 | 2023-06-07 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-07 13:00 | 2023-06-07 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-06-07 17:00 | 2023-06-07 21:00 | Overtime | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-06-07 21:00 | 2023-06-08 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-08 08:00 | 2023-06-08 12:00 | Morning shift | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-06-08 12:00 | 2023-06-08 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-08 13:00 | 2023-06-08 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1
2023-06-08 17:00 | 2023-06-08 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 1
2023-06-08 21:00 | 2023-06-09 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-09 08:00 | 2023-06-09 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1
2023-06-09 12:00 | 2023-06-09 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-09 13:00 | 2023-06-09 17:00 | Afternoon shift | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-06-09 17:00 | 2023-06-10 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-10 08:00 | 2023-06-11 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-11 08:00 | 2023-06-12 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-12 08:00 | 2023-06-12 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-06-12 12:00 | 2023-06-12 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-12 13:00 | 2023-06-12 17:00 | Afternoon shift | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1
2023-06-12 17:00 | 2023-06-13 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-13 08:00 | 2023-06-13 12:00 | Morning shift | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-06-13 12:00 | 2023-06-13 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-13 13:00 | 2023-06-13 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-06-13 17:00 | 2023-06-14 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-14 08:00 | 2023-06-14 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-06-14 12:00 | 2023-06-14 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-14 13:00 | 2023-06-14 17:00 | Afternoon shift | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-06-14 17:00 | 2023-06-15 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-15 08:00 | 2023-06-15 12:00 | Morning shift | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1
2023-06-15 12:00 | 2023-06-15 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-15 13:00 | 2023-06-15 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
2023-06-15 17:00 | 2023-06-16 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-16 08:00 | 2023-06-16 12:00 | Morning shift | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1
2023-06-16 12:00 | 2023-06-16 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-16 13:00 | 2023-06-16 17:00 | Afternoon shift | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1
2023-06-16 17:00 | 2023-06-16 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1
2023-06-16 21:00 | 2023-06-17 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-17 08:00 | 2023-06-18 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-18 08:00 | 2023-06-19 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-19 08:00 | 2023-06-19 12:00 | Morning shift | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1
2023-06-19 12:00 | 2023-06-19 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-19 13:00 | 2023-06-19 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-06-19 17:00 | 2023-06-20 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-20 08:00 | 2023-06-20 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1
2023-06-20 12:00 | 2023-06-20 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-20 13:00 | 2023-06-20 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-06-20 17:00 | 2023-06-20 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-06-20 21:00 | 2023-06-21 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-21 08:00 | 2023-06-21 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-06-21 12:00 | 2023-06-21 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-21 13:00 | 2023-06-21 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1
2023-06-21 17:00 | 2023-06-22 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-22 08:00 | 2023-06-22 12:00 | Morning shift | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1
2023-06-22 12:00 | 2023-06-22 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-22 13:00 | 2023-06-22 17:00 | Afternoon shift | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-06-22 17:00 | 2023-06-22 21:00 | Overtime | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1
2023-06-22 21:00 | 2023-06-23 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-23 08:00 | 2023-06-23 12:00 | Morning shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-06-23 12:00 | 2023-06-23 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-23 13:00 | 2023-06-23 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1
2023-06-23 17:00 | 2023-06-24 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-24 08:00 | 2023-06-25 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-25 08:00 | 2023-06-26 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-26 08:00 | 2023-06-26 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 1
2023-06-26 12:00 | 2023-06-26 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-26 13:00 | 2023-06-26 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1
2023-06-26 17:00 | 2023-06-27 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-27 08:00 | 2023-06-27 12:00 | Morning shift | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-06-27 12:00 | 2023-06-27 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-27 13:00 | 2023-06-27 17:00 | Afternoon shift | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-06-27 17:00 | 2023-06-28 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-28 08:00 | 2023-06-28 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-06-28 12:00 | 2023-06-28 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-28 13:00 | 2023-06-28 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1
2023-06-28 17:00 | 2023-06-29 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-29 08:00 | 2023-06-29 12:00 | Morning shift | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1
2023-06-29 12:00 | 2023-06-29 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-29 13:00 | 2023-06-29 17:00 | Afternoon shift | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-06-29 17:00 | 2023-06-29 21:00 | Overtime | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-06-29 21:00 | 2023-06-30 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-30 08:00 | 2023-06-30 12:00 | Morning shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-06-30 12:00 | 2023-06-30 13:00 | Lunch break | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023-06-30 13:00 | 2023-06-30 17:00 | Afternoon shift | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1
2023-06-30 17:00 | 2023-06-30 21:00 | Overtime | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2023-06-30 21:00 | 2023-07-01 08:00 | Rest times | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0